## Sheet1
NO less than previous earned value on dedicated budget with 10% added safty
action_plan
| per_plan | cum_plan | cum_plan - cum_ev | assignment | per_actual | cum_actual | rand | per_ev | cum_ev | cum_overrun | per_remain | cum_remain | spi | cpi
0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.047619 | 0.047619 | 0.047619 | 1 | 0.047619 | 0.047619 | 0.94 | 0.044762 | 0.044762 | 0 | 0.0028571 | 0.0028571 | 0.94 | 0.94
2 | 0.047619 | 0.095238 | 0.050476 | 0.84 | 0.060091 | 0.10771 | 0.96 | 0.057687 | 0.10245 | 0.012472 | -0.010068 | -0.0072109 | 1.0757 | 0.95116
3 | 0.047619 | 0.14286 | 0.040408 | 0.82 | 0.049278 | 0.15699 | 0.92 | 0.045336 | 0.14778 | 0.014131 | 0.0022831 | -0.0049278 | 1.0345 | 0.94138
4 | 0.095238 | 0.2381 | 0.09031 | 0.74 | 0.12204 | 0.27903 | 0.84 | 0.10251 | 0.2503 | 0.040934 | -0.0072763 | -0.012204 | 1.0513 | 0.89704
5 | 0.095238 | 0.33333 | 0.083034 | 0.71 | 0.11695 | 0.39598 | 0.81 | 0.094729 | 0.34503 | 0.062645 | 0.00050916 | -0.011695 | 1.0351 | 0.87133
6 | 0.14286 | 0.47619 | 0.13116 | 0.71 | 0.18474 | 0.58071 | 0.84 | 0.15518 | 0.50021 | 0.10452 | -0.012321 | -0.024016 | 1.0504 | 0.86136
7 | 0.14286 | 0.61905 | 0.11884 | 0.71 | 0.16738 | 0.7481 | 1 | 0.16738 | 0.66759 | 0.12905 | -0.024525 | -0.048541 | 1.0784 | 0.89238
8 | 0.14286 | 0.7619 | 0.094316 | 0.71 | 0.13284 | 0.88094 | 0.9 | 0.11956 | 0.78714 | 0.11903 | 0.023301 | -0.02524 | 1.0331 | 0.89353
9 | 0.095238 | 0.85714 | 0.069999 | 0.71 | 0.098589 | 0.97953 | 1 | 0.098589 | 0.88573 | 0.12238 | -0.0033514 | -0.028591 | 1.0334 | 0.90425
10 | 0.047619 | 0.90476 | 0.019028 | 0.71 | 0.0268 | 1.0063 | 0.9 | 0.02412 | 0.90985 | 0.10156 | 0.023499 | -0.005092 | 1.0056 | 0.90413
11 | 0.047619 | 0.95238 | 0.042527 | 0.71 | 0.059897 | 1.0662 | 0.93 | 0.055704 | 0.96556 | 0.11384 | -0.0080854 | -0.013177 | 1.0138 | 0.90559
12 | 0.047619 | 1 | 0.034442 | 0.71 | 0.048509 | 1.1147 | 0.89 | 0.043173 | 1.0087 | 0.11473 | 0.0044457 | -0.0087317 | 1.0087 | 0.90491
| 1 | TRUE |  |  | 1.1147 | TRUE |  | 1.0087 | TRUE
we start at the first timestep, asign the first s-curve plan, according to worst (or any method of prediction and adjustment for the future) ratio of Earned value according to the actual allocation we set the next allocation requirement. so ACWP_t1 = S_curve_t1 BCWP_t1 = some portion of ACWP_t1 and then we would estimate for the next ACWPs according to the ration of BCWP/ACWP, meaning: ACWP_t2 = [(S_curve_t2 + S_curve_t1) - (BCWP_t1)]/ (BCWP_t1/ACWP_t1) so we approximate the required budget for each timestep by adjusting this ratio of remained plan. * and then at each timestep we evaluate the expected gains using NPV methods for received payments and the required budgets. -------------- For true learning under uncertainty, we simulate uncertainty and compute the optimal solution using convex optimization, yet the agent is unaware of the future outcomes of it's allocation action. In the benchmark we will calculate the budgeting requirements for each project at each timestep using random earned value to actual allocation ratios. These ratios are prevenerated and earned value for each allocation amount is determined. Then using optimization methods we calculate the optimal allocation for each timestep. In other words we calculate the optimal allocation portion of each timestep's budgeting requirement to maximize the gains of portfolio over the timespan of the portfolio. The agent unaware of the future, unaware of the earned value with respect to the actual allocated budget at that timestep will learn to maximize the gains only by having the history of previous allocations and the original contractual information. At the end of the training the gains and quality of agent's action's in each scenario will be compared with the benchmark. (Such as Mean stats for the Last 100 episodes.)
Note on L24: Mahriar Gharaghani: over allocation, Trunkated budget