## Sheet1
NO less than previous earned value on dedicated budget with 10% added safty
action_plan
| per_plan | cum_plan | cum_plan - cum_ev | assignment | per_actual | cum_actual | rand | per_ev | cum_ev | cum_overrun | per_remain | cum_remain | spi | cpi
0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0.047619 | 0.047619 | 0.047619 | 1 | 0.047619 | 0.047619 | 0.82 | 0.039048 | 0.039048 | 0 | 0.0085714 | 0.0085714 | 0.82 | 0.82
2 | 0.047619 | 0.095238 | 0.05619 | 0.72 | 0.078042 | 0.12566 | 0.99 | 0.077262 | 0.11631 | 0.030423 | -0.029643 | -0.021071 | 1.2212 | 0.92558
3 | 0.047619 | 0.14286 | 0.026548 | 0.72 | 0.036872 | 0.16253 | 0.87 | 0.032078 | 0.14839 | 0.019676 | 0.015541 | -0.0055308 | 1.0387 | 0.91297
4 | 0.095238 | 0.2381 | 0.089707 | 0.72 | 0.12459 | 0.28713 | 0.88 | 0.10964 | 0.25803 | 0.049031 | -0.014404 | -0.019935 | 1.0837 | 0.89866
5 | 0.095238 | 0.33333 | 0.075303 | 0.72 | 0.10459 | 0.39171 | 0.95 | 0.099358 | 0.35739 | 0.058381 | -0.0041202 | -0.024055 | 1.0722 | 0.91237
6 | 0.14286 | 0.47619 | 0.1188 | 0.72 | 0.165 | 0.55672 | 0.86 | 0.1419 | 0.49929 | 0.080527 | 0.00095478 | -0.0231 | 1.0485 | 0.89685
7 | 0.14286 | 0.61905 | 0.11976 | 0.72 | 0.16633 | 0.72305 | 0.94 | 0.15635 | 0.65564 | 0.104 | -0.013492 | -0.036592 | 1.0591 | 0.90678
8 | 0.14286 | 0.7619 | 0.10626 | 0.72 | 0.14759 | 0.87064 | 1 | 0.14759 | 0.80323 | 0.10873 | -0.0047329 | -0.041325 | 1.0542 | 0.92258
9 | 0.095238 | 0.85714 | 0.053913 | 0.72 | 0.074879 | 0.94551 | 0.94 | 0.070386 | 0.87362 | 0.088372 | 0.024852 | -0.016473 | 1.0192 | 0.92396
10 | 0.047619 | 0.90476 | 0.031146 | 0.71 | 0.043867 | 0.98938 | 0.81 | 0.035532 | 0.90915 | 0.08462 | 0.012087 | -0.0043867 | 1.0048 | 0.91891
11 | 0.047619 | 0.95238 | 0.043232 | 0.71 | 0.060891 | 1.0503 | 0.86 | 0.052366 | 0.96151 | 0.097892 | -0.0047469 | -0.0091336 | 1.0096 | 0.91549
12 | 0.047619 | 1 | 0.038485 | 0.71 | 0.054205 | 1.1045 | 0.89 | 0.048242 | 1.0098 | 0.10448 | -0.00062328 | -0.0097569 | 1.0098 | 0.91424
| 1 | TRUE |  |  | 1.1045 | TRUE |  | 1.0098 | TRUE
we start at the first timestep, asign the first s-curve plan, according to worst (or any method of prediction and adjustment for the future) ratio of Earned value according to the actual allocation we set the next allocation requirement. so ACWP_t1 = S_curve_t1 BCWP_t1 = some portion of ACWP_t1 and then we would estimate for the next ACWPs according to the ration of BCWP/ACWP, meaning: ACWP_t2 = [(S_curve_t2 + S_curve_t1) - (BCWP_t1)]/ (BCWP_t1/ACWP_t1) so we approximate the required budget for each timestep by adjusting this ratio of remained plan. * and then at each timestep we evaluate the expected gains using NPV methods for received payments and the required budgets. -------------- For true learning under uncertainty, we simulate uncertainty and compute the optimal solution using convex optimization, yet the agent is unaware of the future outcomes of it's allocation action. In the benchmark we will calculate the budgeting requirements for each project at each timestep using random earned value to actual allocation ratios. These ratios are prevenerated and earned value for each allocation amount is determined. Then using optimization methods we calculate the optimal allocation for each timestep. In other words we calculate the optimal allocation portion of each timestep's budgeting requirement to maximize the gains of portfolio over the timespan of the portfolio. The agent unaware of the future, unaware of the earned value with respect to the actual allocated budget at that timestep will learn to maximize the gains only by having the history of previous allocations and the original contractual information. At the end of the training the gains and quality of agent's action's in each scenario will be compared with the benchmark. (Such as Mean stats for the Last 100 episodes.)
Prove that considering drawbacks and benifits of both sides and use weights for them to prove the agent is as good as the benchmark, which is knowing the future. It's almost as good as the future. * implementing convex optimization on allocation decisions over the portfolio timespan. knowing the future values and solving for optimal solution gives the ultimate benchmark to evaluate the agent's policy. * for evaluating the agent's policy we have to consider all the positive concervativeness of not knowing the future and increase the weghts of it's parameter in scoring it relative to the optimal solution. * the agent must establish obvious patterns of learning and then at the last 100 episodes we must evaluate it's response with the benchmark for those episodes and report the conclusion as a mean of the final states. ---- Use the data from the previous year of S&P500 for one implementation of uncertainty for payments as the market value is the best indicator of the major status of a company. also it's a relatively good data set. ____
Note on L24: Mahriar Gharaghani: over allocation, Trunkated budget